## Sheet1
IFB299 Gantt Chart Group 44
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13
[6 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
User Stories, Release & Sprint Planning
| Identify Features (MOSCOW) | 2018-07-26 | 2018-07-30 | 3 | 100% | bar: WEEK 1 Th to WEEK 2 W; WEEK 4 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Create User Stories | 2018-08-02 | 2018-08-13 | 8 | 80% | bar: WEEK 2 M to WEEK 2 T; WEEK 2 Th to WEEK 4 M; WEEK 4 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Create Release Planning | 2018-08-16 | 2018-08-17 | 2 | 60% | bar: WEEK 4 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Create Sprint Planning | 2018-08-20 | 2018-08-23 | 4 | 40% | bar: WEEK 4 W; WEEK 5 M to WEEK 5 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
Sprint 1
| Create Computer Architecture Designs | 2018-08-30 | 2018-09-03 | 3 | 100% | bar: WEEK 4 W; WEEK 5 Th to WEEK 6 M; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Wireframing (Low - Med fidelity) | 2018-09-06 | 2018-09-10 | 3 | 80% | bar: WEEK 4 W; WEEK 6 Th to WEEK 7 M; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Initial Development Stage | 2018-09-04 | 2018-09-19 | 12 | 60% | bar: WEEK 4 W; WEEK 7 T to WEEK 9 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Software Testing | 2018-09-10 | 2018-09-19 | 8 | bar: WEEK 4 W; WEEK 8 M to WEEK 9 W; WEEK 10 M; WEEK 12 Th to WEEK 13 M
| Correct Issues | 2018-09-20 | 2018-09-21 | 2 | 40% | bar: WEEK 4 W; WEEK 9 Th to WEEK 10 M; WEEK 12 Th to WEEK 13 M
Sprint 2
| Wireframing | 2018-10-02 | 2018-10-03 | 2 | 100% | bar: WEEK 4 W; WEEK 10 M to WEEK 10 W; WEEK 12 Th to WEEK 13 M
| Design Layout | 2018-10-04 | 2018-10-22 | 13 | 80% | bar: WEEK 4 W; WEEK 10 M; WEEK 10 Th to WEEK 13 M
| Development | 2018-10-11 | 2018-10-22 | 8 | 60% | bar: WEEK 4 W; WEEK 10 M; WEEK 11 Th to WEEK 13 M
| Software Testing | 2018-10-18 | 2018-10-24 | 5 | 40% | bar: WEEK 4 W; WEEK 10 M; WEEK 12 Th to WEEK 13 W
| Correct Issues | 2018-10-22 | 2018-10-24 | 3 | 20% | bar: WEEK 4 W; WEEK 10 M; WEEK 12 Th to WEEK 13 W
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])